## English
RURAL ROAD DEVELOPMENT PROJECT-KURUNEGALA DISTRICT(RS.MN.60) 2019
MINISTRY OF HOUSING,CONSTRUCTION AND CULTURAL AFFAIRS
DS DIVISION - Nikaweraitya |  |  |  | 2019.07.01
S.No | Name of the project | G.N.Division | Estimated Cost (Rs) | Allocation (Rs) | Length/(m/Km) | Implimenting Agency | Name of the Contractor/Society | Progress
[8 empty] | Financial |  | Physical
[8 empty] | Expenditure(Rs) | % | A | B1 | B2 | B3 | B4 | C | D | E | F | G
1 | Concreting Budumuththawa Road | Budumuththawa | 981022.05 | 990000 | 80.10m | DS Nikaweratiya | Samurdhi Community based society Budumuttawa | 980000 | [10 empty] | 1
2 | Concreting Walpolagama to Deduruoya cannel Road | Divullegoda | 981450.36 | 990000 | 96m | DS Nikaweratiya | Walpolagama Farmer Organization | 980000 | [10 empty] | 1
3 | Concreting Balagolla Ihakolagama Road | Ihakolagama | 980623.56 | 990000 | 101.20m | DS Nikaweratiya | Mahasen Rural Development Sciety | 980000 | [10 empty] | 1
4 | Concreting Hulogedara Galwadugama road infront of the School | Hulogedra | 980492.72 | 990000 | 96.80m | DS Nikaweratiya | Pragathi Grama Sanwardana Samithiya | [8 empty] | 1
5 | Concreting Pinnapolegama Kumburupitiya road starting from Mr.Lasantha's house to Mr.Thennakoon house | Pinnapolegama | 980492.72 | 990000 | 96.80m | DS Nikaweratiya | Govi Sanvidanaya pinnapolegama | [9 empty] | 1
6 | Concreting Wiwaranagala temple road | Halmillewa | 980633.27 | 990000 | 116m | DS Nikaweratiya | [8 empty] | 1
7 | Conreting Nebadewa Dunukedeniya road | Nebedewa | 980633.27 | 990000 | 116m | DS Nikaweratiya | [8 empty] | 1
| Total |  | 6865347.95 | 6930000 |  |  |  | 2940000 |  | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 3
| Prepard By …………….. |  |  |  | Cheked by………………….. |  |  |  | Approved by…………………..
| Development Assistant |  |  |  | AD(Planning) |  |  |  | Divisional Secretary
** Physical Progress
| A | Estimate is being/to be prepared |  |  |  |  | D | 60% completed
| B1 | Estimates approved & Bid Document prepared |  |  |  |  | E | 80% completed
| B2 | Quation/Bid Called |  |  |  |  | F | 99% completed
| B3 | Quation/Bid received |  |  |  |  | G | 100% completed
| B4 | Cotract Awarded
| C | Start construction work, 40% completed