## Sheet1
Rural Infrastructure Development Programme (RIDP) - 2019
Physical and Financial Progress of the Month of 2019/07/01
District : Kurunegala
No | Name of the Project | DS Division | GN Division |  | Name Of Minister/Member of Parliament/officer who propoesd the project | Length(k.m/m.)/ Area (/sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress | [11 empty] | No. of Beneficiaries | Remarks
|  |  |  | Sector | [5 empty] | Financial |  | Physical **
[10 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
| Water extention (about 800m) for Kurunegala Puttlam Main road to Elawaka Kohu Mola road |  | 320 Elawaka | WS |  |  | 500000 |  |  |  |  | 1
| Sub total | [5 empty] | 500000 |  |  |  |  | 1
| Greveling road starting from near by Hulugalla community hall second lane |  | 310 Hulugalla | RA |  | 435m | 500000 | DS Nikaweratiya | Hulugalal Grama sanvardana Samithiya | [7 empty] | 1 |  |  |  |  | 20
| Mortergradering and greveling Hewenpelessa Thekka kotuwa to Aluth wewa road |  | 299 Hewanpelessa | RA |  | 240m | 500000 | DS Nikaweratiya | Hewanpelessa Garama Sanwardana Samithiya | [7 empty] | 1 |  |  |  |  | 80
| Sub total | [5 empty] | 1000000 | [9 empty] | 2 |  |  |  |  | 100
| Construction of roof in Palu Thimbiriyawa Community hall |  | 315 Thimbiriyawa | LD |  |  | 500000 | DS Nikaweratiya | Grama Sanwardana Samithiya | [7 empty] | 1 |  |  |  |  | 60
| Sub total | [5 empty] | 500000 | [9 empty] | 1 |  |  |  |  | 60
| Renovation of Hulogedara Kuda wewa |  | 321 hulogedara | AI |  |  | 500000 | DS Nikaweratiya | Hulogedara Govi Sanvidanaya | [11 empty] | 1 | 15
| Sub total | [5 empty] | 500000 | [13 empty] | 1 | 15
| Total | [5 empty] | 2500000 |  |  |  |  | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 1 | 175